Global Matrix 4.0 Report Card Country Leader Survey: Mid-Development

Summary of Responses

In November of 2021, the Active Healthy Kids Global Alliance (AHKGA) disseminated a survey titled “Global Matrix 4.0 Report Card Country Leader Survey: Mid-development”, which focused on Report Card teams’ experience from the beginning until mid-stages (January 2020 - November 2021) of their participation in the Global Matrix 4.0 project. The survey was completed by 97% of the targeted respondents (i.e., one Report Card leader per participating team, n=60). The results are summarized below.

The majority of Report Card country leaders reported their progress with the Report Card development as being on time (56.9%) versus being ahead (19%) or behind (24.1%) of the recommended schedule. Of the survey respondents, 84.5% stated that the process was disrupted (ranging from a small to an extremely large extent) by the COVID-19 pandemic.

The number of people on the Report Card development team/working group ranged from 1 to 40, with the most common team size being 6 to 20 people (67.2%). The majority of Report Card country leaders felt that their Report Card team was the right size (77.5%), had the right composition of people (81%), and was functioning effectively and efficiently (84.5%). Some changes were made since the initial establishment of the teams: 32.8 % of leaders reported that one or more members of their Report Card teams were removed or quit and 44.8% of teams added new member(s). The most common reason of drop out was a move of a team member to another position/city/country or retirement; the addition of new members was primarily due to the expertise needed for the Report Card.  About one-third of respondents (32.8%) reported being concerned about missing important representation on their Report Card team, mainly in communication/marketing, community design/built environment, and government sectors.

When asked about the collection of data/information for the Report Card, the majority of participants responded “strongly agree” or “agree” that the evidence-gathering process in their country was suitable for the Report Card (82.8%) and functioned effectively and efficiently (77.6%), and that data sources in their country were of good quality (58.6%) and broadly representative of the country (58.6%). Of survey respondents, 48.3% indicated that there was no systematic surveillance system of physical activity in their country and 58.6% stated that they systematically use an international surveillance system for physical activity (e.g., HBSC, GSHS). More than one-third of Report Card teams (34.5%) conducted their own data collection for their country's Report Card.  The majority of respondents (79.3%) felt that there were research gaps that affected their ability to assign grades. Regarding the age range, Report Card leaders reported that the data sources/studies used to inform grades covered children (5-12 years old) (86.2%) and adolescents (13-17 years old) (96.6%).  The survey respondents expected their grades to be informed by data pre-COVID restrictions (84.5%), during COVID restrictions (29.3%), and/or post-COVID-19 restrictions (12.1%) (respondents could select more than 1). Of the survey participants, 56.9% were planning to include additional indicators in their country Report Card (e.g., obesity, sleep, diet, physical literacy) and 31% were going to report subgrades (e.g., early years, gender, children with disabilities/special needs).

In terms of the synthesis/interpretation of information and suitability of benchmarks, the majority of respondents indicated that the data synthesis and interpretation process was functioning effectively and efficiently for their country (81%) and that the benchmarks provided were appropriate (87.9%). The survey participants felt “very confident” (67.2%) or “somewhat confident” (29.3%) about the quality of the data synthesis and interpretation in their Report Card.

When asked which AHKGA’s communications they appreciate/value the most, the respondents selected the Global Matrix 4.0 e-blasts (87.9%), individual emails (53.4%), website postings (36.2%), and messages on social media (25.9%) (respondents could select more than 1). Report Card leaders reported that they “often” or “sometimes” read the Global Matrix 4.0 monthly e-blasts (100%), checked the AHKGA website for updates (87.9%), and used the "Member Area" section of the website (89.6%). Of survey respondents, 75.9% followed AHKGA’s social media/networking accounts. Among followers, Twitter was the most popular platform for AHKGA and Global Matrix-related communications (86.4%) compared to ResearchGate (31.8%), Facebook (27.3%), and LinkedIn (25%) (respondents could select more than 1).

At the time of the survey, 44.8 % of respondents reported that they had funding to develop and produce their Report Card, and 19% expected to have funding to attend the Global Matrix 4.0 release event in Abu Dhabi.

Regarding the level of satisfaction with the Global Matrix 4.0 project development, the majority of survey respondents reported being “supportive” or “very supportive” of the Global Matrix 4.0 release date of October 24-27, 2022 (87.9%), of the Global Matrix 4.0 release location of Abu Dhabi, UAE (62.1%), and of the decision to release the Global Matrix 4.0 in conjunction with the ISPAH 2022 Congress (84.5%). At the time of the survey, about half of respondents (51.8%) said that they were “likely” or “very likely” to attend the Global Matrix 4.0 release event in person. According to survey results, 87.9 % were satisfied with the publication plan for the Global Matrix 4.0.

Overall, 94.8 % reported being “very satisfied” or “satisfied” with being part of the Global Matrix 4.0 so far. General comments included some concerns (e.g., challenges to data interpretation, comparison, and dissemination introduced by the COVID-19 situation), suggestions for the future (e.g., extension to include early years) as well as positive feedback (e.g., prompt and helpful guidance from the AHKGA).

AHKGA would like to thank survey participants for their valuable feedback!